# Sustainable development plan

# Protochnoe village municipality

# 2005-2010

# Table of contents

History and description of Protochnoe village, Liman raion, Astrakhan oblast	3

Description of planning process	5

Vision	6

Main problems	7

SWOT analysis	8

Priorities and action plans	9

Resources needed	10

CSD Plan monitoring and implementation	13

Appendix 1  List of members of the CCP	14

Appendix 2. Questionnaires	15

# History and description of Protochnoe village, Liman raion, Astrakhan oblast

Protochnoe village locates in the northern part of the Liman raion, Astrakhan oblast. Eighty years ago in 1923 fishermen’s families settled in this small corner of this free steppe area and the village of Bantir was established (now Protochnoe village). The name of the village originated from the name of a rich Kalmykian – Bantir who had fisheries business. People from the neighboring villages came to his to get a job but it was not convenient to travel to work every day. Therefore many people decided to move and live in Venderevo and Bantir villages.

The first mentioning about Bantir village was found since 1923 in the records of Mikhanilovski village community, Yandykovski raion, Astrakhan oblast. The name of the Bantir village was changed into Protochnoe of the Liman raion in 1953.

The village located on elevated area extended from the east to west along the Zenzelinski canal surrounded with water bodies which positively affects the microclimate in the village.   The water bodies’ area is 2.7 thousand ha.

Two zones may be clearly distinguished in the village – residential and production. Residential zone includes one-storeyed houses with homesteads.

In the Protochnoe village there are 229 farms. Population constitutes 629 people of which:

- able-bodied population - 315 people or 50% of total population;

- pensioners - 151 people or  24% of total population;

- children from 0 to 18 years old – 163 people, or 26%. of total population;

Average income of able-bodied population is about 1000 rubles.

Houses locate on three streets: Oktyabrskaya, Kooperativnaya and Molodezhnaya. The central street is Oktyabrskaya where there are all administrative and socio-cultural buildings:

- Administration of the Protochnoe village municipality;

- Culture House

- Secondary school

- Post office.

Parallel to Oktyabrskaya there is Kooperativnaya street with medical and obstetric staion with physiotherapeutic and massage wards but due to the lack of finances this may be soon closed.

At the entrance to the village from the western side there is a block of new houses and kindergarten “Rucheek”. This street is called Molodezhnaya. More then half of the street is engaged with houses made of bricks and there are some old houses made of framed reeds. Roofs are covered with slates.

There are 5 shops in the village. One of them is a grocery store, another tree are for day-to-day goods and one more is a household shop. There is a mini bakery providing bakery products to people from Protochnoe and other neighboring villages. There are also two bars.

Able-bodies population work in social and cultural village organizations and in the State Farm “40 years of October” although the state farm activity does not develop due to lack of support. Despite of some difficulties and failures in agriculture sector people in Protochnoe are searching for new ways of agriculture development. They do not lose their hearts and grow potato, tomato and other production.

Practically in every village yard there is a private subsidiary plot (PSP). Thus, in PSPs there are 163 cattle including 74 cows, 574 sheep, 18 pigs, and various poultry. In summer villagers are mainly engaged in growing tomato. In 2004 they produced 555 tonnes of tomato.

The village is fully supplied with gas. Electrical network operates properly, roads are covered with asphalt, water supply pipeline runes but sometimes it is switched off due to lack of finances. The majority of young people is unemployed and relies only on their private plots but here they also have some difficulties. They produce excellent production but cannot sell it and prices are dictated by purchasing agents. It is so much desired that in the village there would be a mini plant for vegetable processing and hence there would be new jobs and young people would not leave the village.

The village administration in its work pays attention to improvements in the village and establishing proper order in there. At present, the Protochnoe village is one of the most improved in the raion. There is a plan to arrange and improve the village beach, one of the most favorite places of children in summer. Works are done on utilization of domestic waste and special days of sanitary cleaning are organized. Annually there is a competition held on the best yard. Village people work actively on planting and improvements of their yards. Front sides of yards are beautifully decorated, there are fruit and other trees planted in the yards and small gardens – all this gives the village the attractive architectural image and pleases villagers and visitors.

# Description of planning process

Elaboration of strategic sustainable development plan of the Protochnoe municipality was implemented within the EC CEP Project “Sustainable development of Caspian Coastal Communities in Azerbaijan, Kazakhstan, Russia and Turkmenistan” The date of November 26 2004 was the first step of its preparation when active leaders from the village and raion representatives took part in the workshop on sustainable development implemented by IMC Consulting.

In order to elaborate the plan by the community a certain work was done lsuch as establishment of Coordination Committee on Planning (CCP) comprising of 6 leaders (list of Committee members is in Appendix 1). At the first meeting of CCP its members worked out the schedule of work, discussed the most important aspects and problems to pay attention to during the planning process, determined social groups of village people. During several months practically all villagers were involved in the planning process.

In order to collect information informal meetings were conducted with all social groups in school with teachers and schoolchildren, in kindergarten “Rucheek” with parents and teachers, in administration with entrepreneurs and PSP owners, in club and library with other people. In the work with population various planning methods were applied like drawing diagrams, charts and schemes. In the kindergarten a competition was conducted devoted to the theme “My small motherland – Liman raion” and the three best drawings were chosen for participation in the raion competition. Open general meetings were implemented where population was informed about the work on Community Sustainable Development Plan. The Committee organized a postal named “Your proposals for sustainable development of our village” with photos of village objects. People had a chance to choose the most important subjects and write their ideas and proposals on improvements.

Over 200 questionnaires were distributed among villagers. Those were questionnaires for adult population (no. 1) and young people (No. 2). Text of questionnaires is provided in Appendix 2).

Analysis of questionnaires results showed the following:

Questionnaire No.1:

- 81% of people hope that CSD plan will help them;

- urgent problems of people’s concern are low incomes, lack of jobs, high prices and their growth and at the same time low prices for agricultural production grown by villagers (tomato) as in their growing about 96% of population are engaged.

Questionnaire No. 2:

- 52% of young people knew about the CSD plan preparation at the meeting, 7% - from the raion newspaper article;

- 93% of young people wish to participate in planning process;

- 71% of young people hope that CSD Plan will help them to improve their lives;

- new jobs, entertainments, places for sports, arts, culture development, access to information including internet are assessed by young people as “poor” and “very poor”, activity of cafe was assessed as satisfied;

- problems existing among young people are – alcoholism, drags;

- a question “What can prevent young people from leaving the village” most answered  parental relations and new jobs.

Based on results of work with population a future vision of the Protochnoe village was developed, SWOT analysis implemented, weakness, strength, opportunities and threats were identified. Then main directions of development, priority projects for life improvement and action plans for their implementation were determined.

# Vision

As we are citizens if this village its every change is important for us. We wish to see our village in ten years with improved life quality of people, developed economy. We would like to see many children running in the village and hear their laugh everywhere. We would like to see blossoming gardens and in the mornings hear cocks’ crows from all yards as it is supposed to be in the village. There will be a new plant for vegetable processing, agricultural activity rehabilitated including the state farm. Not only young people but also older ones will have jobs and opportunities for culture and pleasure. People going to work in the morning will know that their labor will be assessed accordingly. New housed will be built for young specialists and young families. Medical services will be of excellent quality therefore population will be always healthy. And healthy population means robust future.

# Main problems

During planning process 5 main problems were revealed as follows:

1.     Young people leaving the village

Main causes of the problem that young people leave the village are absence jobs, houses, low level of social and cultural life of the population. However, there are young people who have strong relations and continue live in the village. It turned out so that during many decades in our village the whole dynasties of native people live which continuously grow. Young families develop wishing to stay in the native village and continue their parents’ business. Many of them stay regardless of difficulties and complicated conditions under which they have to live and survive.

2. Absence of enterprises developing economy

In the village there are all prerequisites for development of small and medium business. There are fish resources – the main basis for fishing enterprises development; water resources of total area 2700 ha; lands and pastures of 5900 ha area for growing agricultural production, there are raw materials for production of construction goods (clay and reeds to make air bricks), attractive landscapes, water bodies and biological resources for tourism development. There are all conditions and engineering infrastructure for establishment of mini plants for processing of agricultural products. Development of small business and agriculture is constrained by imperfection of crediting system, lack of organized sales of agricultural products (sales of tomato goes on spontaneously without control of prices), weak activity of marketing services.

3. Low social and cultural level in the village

There are social objects in the village but all of them need improvements.

Club

The club is in emergency state due to lack of financing from the raion and oblast administrations. It is necessary to purchase music instruments and organize work of hobby groups, involve specialists (musician).

Secondary school

It is necessary to establish and equip computer class, purchase text books, exercise books, make major repair of the building, construct a sports ground and purchase all necessary sport equipment. All this require financing.

Kindergarten “Rucheek”

Financing is needed for installation of technical water pipeline, major repair and purchase of necessary textbooks and toys.

Medical and obstetric station

Regardless of the availability of good specialists it is under the threat of closing due to lack of financing. In the village there are no pharmacy shops and dentist which is urgently needed for standard medical services provision.

4. Unsatisfactory state of the road and bridge

Financing is needed from the federal budget.

5. Ecological problems

Ecological problems include overgrowing of water bodies with reeds and absence of organized system for waste collection and processing. In order to organize cutting the reeds in rivers and canals machinery and finances are needed.

# SWOT analysis

SWOT analysis is determination of strength and weakness of the community and external opportunities and threats. Sources used during implementation of SWOT analysis included information presented during social and economic analysis, knowledge of population accumulated during meetings.

Internal strength of the community

- Availability of natural resources (lands, water, reeds, biological resources);

- Favorable conditions for vegetable growing (climate, water resources, lands – all this is suitable for growing tomato, pepper, water melon);

- Availability of internal water bodies;

- Engineering infrastructure for small business development (technical water, power supply, gas supply);

- Availability of active people wishing to change the life in the village to the better;

- Strong relative relations of villagers.

Internal weakness of the community

- Lack of internal investments;

- Poor development of village economy resulting in poaching for subsistence.

External opportunities

- Existence of positive trends of economic activity in the country and increasing demand for products produced in the municipality;

- Changes in legislation related to development and strengthening of municipal budgets;

- Attraction of investments into agricultural sector;

- Construction of highway Zarechnoe-Protochnoe-Mikhailovka;

- Increase of attractiveness of various small businesses for local population;

- Support from the raion and oblast administrations;

- Mortgage system for young families for purchase and construction of houses;

- Study of other territories’ experience related to sustainable development.

External threats

- Poor work of the marketing services and market infrastructure (prices are dictated);

- Inability to involve and retain qualified personnel;

- Imperfection of provisions regulating fishing;

- Ecological threat like overgrowth of rivers and canals with reeds.

# Priorities and action plans

Priority 1 – Development of economy and small business

- Establish small enterprise on processing agricultural production (tomato)

- Establish a station for delivering and reception of vegetables;

- Establish a poultry farm;

- Establish an enterprise for producing construction materials of local resources (reeds, clay);

- Develop enterprises on souvenirs production in order to employ people in winter;

- Develop fisheries enterprises.

Priority 2 – Development of social and cultural life in the village

- Implement repair of the club, purchase music instruments, involve specialist-musician to work in the village;

- Organize work of hobby groups and center for festivals implementation;

- Organize construction of road, bridge and reconstruction of village roads and pavements;

- Organize construction of sport ground on a basis of school;

- Install technical water pipeline in the kindergarten;

- Establish a pharmacy shop;

- Involve a specialist-dentist to work in the village.

Priority 3 – Improvement of ecological state in the village

- Organize cutting of reeds in rivers and canals in order to improve their ecological state and increase current which will assist to fish passage;

- Organize a system for waste collection and utilization.

# Resources needed

| Priority | Problem | Projects | Resources available | Resources to be leveraged | Finance sources | Output |
| --- | --- | --- | --- | --- | --- | --- |
| Economy – small business development | Lack of jobs and young people leaving the village | Fish farming | - Fish resources in water bodies of 2.7 thousand ha area - Boats - Fish farming experience - Possible production of feeds using own resource base | - Finances for purchase of fry and license (estimated cost 1 million rubles) | - Bank credits - Own finances - Investors - 4. Others | - 1. Establishment of new jobs 2. Provision of people with fish products 3. Provision of fish processing plants with raw fish 4. Possible production of 120 thousand tones of fish per year |
|  |  | Production of construction materials using local reeds | - Local raw – reeds - Workers - Production experience | - Machinery for cutting reeds - Sales - Finances to organize production | - Federal budget (federal target program “Ecology and natural resources”) - Bank credits - Investors - Own finances - Others | 1.Establishment of new jobs 2. Provision of people with construction blocks for building houses and sheds 3. Improvement of ecological state of water bodies |
|  |  | Production of wicker souvenirs using local reeds | - Local raw material - reeds - Workers - Wicker-work experience | 1. Machinery for cutting reeds 2 .Sales 3. Finances to organize production | 1. Federal budget (federal target program “Ecology and natural resources”) 2. Bank credits 3. Investors 4. Own finances | - Establishment of new jobs - Improvement of ecological state of water bodies |
|  |  | Mini plant on tomato processing | - Production buildings - Engineering infrastructure (gas, power and water supply) - Own raw materials - Labor resources | 1. Material contributions, investors | - Own finances - Investors 3. Bank credits | - Establishment of new jobs - Provision of population in the oblast with canned vegetables |
|  |  | Establishment and equipping of a station for delivery and sales of vegetables | 1. Part of construction materials for station establishment 2. Labor resources | 1. Material contributions | 1.Credits 2. Others (Program “Development of Liman Raion Municipality up to 2007”) | 1. Systematic delivery of vegetables 2. Sales of products 3. Establishment of new jobs 4. Provision of other regions with vegetable production |
|  |  | Poultry farm establishment | 1.Idle buildings 2. Specialists | 1. Material contributions, investors | 1. Investments 2. Own finances 3.Oblast budget 4. Raion budget 5. Bank credits | 1. Establishment of new jobs 2. Provision of population with poultry production |
| Social sphere | Unsatisfactory state of social objects, young people leaving the village | Construction of road, bridge and reconstruction of village roads and pavements | 1. Availability of project and design documentation 2. Availability of part of construction materials (reinforced concrete beams) | 1. Financing of works | 1. Oblast budget 2. Own finances 3. Others (Program “Development of Liman Raion Municipality up to 2007”) | 1. Strengthening of relations with other territories 2. Increase of transport flows through the village 3. Development of production sales 3. Gratitude of drivers as their personal vehicles will serve longer |
|  |  | Establishment of a center for festivals implementation based in village club | 1. Construction materials (180 slates) 2. Finances allocated from the raion budgets amounting 110 thousand rubles in 2006 | 1. Financing for repair and equipping of the club and center 2. Specialists | 1. Oblast budget 2. Raion budget 3. Own finances 4. Others | 1. Improvement of life quality for village young people and as a result reduction of young people flow out of the village 2. Establishment of new jobs 3. Effective use of idle rooms |
|  |  | Establishment of school shops on career-guidance based in school | 1. Rooms 2. Production machines 3. Specialists | 1. Assistance in organization | 1. Own finances 2 Sponsors 3. Investors | 1. Establishment of new jobs 2. Effective use of idle rooms |
|  |  | Construction of sport ground based in school | 1. Ground 2. Labor | 1. Financing for purchase of sport equipment | 1. Oblast budget 2. Raion budget 3. Own finances 4. Sponsors 5. Investors. | 1. Improvement of life quality 2. Improvement of children health |
|  |  | Kindergarten “Rucheek” – construction of technical water pipeline and pump | 1. Basement room 2. Labor | 1. Financing for purchase of construction materials (120 m pipes, special equipment – air-ventilation chamber) | - Raion budget - Oblast budget - Sponsors 4. Own finances (Program “Development of Liman Raion Municipality up to 2007”) | 1. Greening of the territory 2. Improvement of services quality |
|  |  | Medical and obstetric station |  | Financing for repair – estimated cost is 20 thousand rubles | - Oblast budget - Raion budget - Own finances 4. Sponsors 5. Others |  |
| Ecology | Deterioration of ecological situation | Organization of cutting reeds in rivers and canals | 1. Tractors and 2 trailer 2. Labor resources | 1. Machinery for cleaning rivers and canals 2. Financing of works | - 1. Federal budget (federal target program “Ecology and natural resources”) 2. Bank credits 3. Investors 4. Own financing 5. Others | 1. Improvement of local ecology 2. Improvement of current in water bodies and possibility for fish to migrate |
|  |  | Organization of a system for waste collection and utilization |  | 1. Assistance in organizing the system | - Own financing - Sponsors - Others | 1. Village sanitary condition improvement |

# CSD Plan monitoring and implementation

# The Committee will monitor and provide assistance in CSD Plan implementation, in particular:

- Implement measures to encourage small business development in the village

- Elaborate measures to promote priority investment projects

- Assist in attracting investments

- Assist in implementation and participation in the respective oblast and raion target programmes

- Consider and correct CSD Plan on a regular basis

- Inform population in the village about results achieved on a regular basis.

# Appendix 1  List of members of the CCP

- Vladimir Pecherin – head of the Protochnoe village municipality

- Yuzefa Abramova  – teacher of the kindergarten “Rucheek”

- Marina Krasheninnikova – administrator of the Protochnoe village municipality

- Natalia Voronina – administrator of the Protochnoe village municipality

- Valentina Kravchenko – entrepreneur

- Tatiana Dormidonova  – economist of the Liman raion administration

# Appendix 2. Questionnaires

Questionnaire 1 for adults

(Please fill in the questionnaire and hand in to the responsible executor)

Village administration is now working with the plan of sustainable development. This questionnaire was worked out to know people’s opinion about the problems in the village and the opportunities of sustainable development.

Please answer the questions giving a mark or a tick in the square of the answer. This questionnaire is anonymous but if you consider it necessary to tell something about yourself or give your comments, we would be very grateful.

| 1 | Do you know about the sustainable development plan for your community? |  |  |  |  | #### Yes |  |  | No |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | If “yes”, how did you know about it? |  |  |  |  |  |  |  |  |
|  | - was present at the meeting |  |  |  |  |  |  |  |  |
|  | - there was the article in the raion newspaper |  |  |  |  |  |  |  |  |
|  | - different (how exactly?) |  |  |  |  |  |  |  |  |
| 2 | Do you want to take part in writing this plan? |  |  |  |  | #### Yes |  |  | No |
| 3 | How can you assess the activity of writing the plan if it is worked out? |  |  |  |  |  |  |  |  |
|  | We hope that it will help us |  |  |  |  |  |  |  |  |
|  | These are only words, nothing will change |  |  |  |  |  |  |  |  |
|  | It is difficult to say |  |  |  |  |  |  |  |  |
|  | Different (how exactly?) |  |  |  |  |  |  |  |  |
| 4 | Were there any changes in your life in the last year? | Better |  | Worse |  |  | No changes |  |  |
|  | - income |  |  |  |  |  |  |  |  |
|  | - safety in the village |  |  |  |  |  |  |  |  |
|  | - communal sphere |  |  |  |  |  |  |  |  |
|  | - medical service |  |  |  |  |  |  |  |  |
|  | - education |  |  |  |  |  |  |  |  |
|  | - trade |  |  |  |  |  |  |  |  |
|  | - consumer services |  |  |  |  |  |  |  |  |
|  | - different (how exactly?) |  |  |  |  |  |  |  |  |
| 5 | What forms of collecting people’s opinion about the most important problems do the local authorities use? |  |  |  |  |  |  |  |  |
|  | - regular questioning |  |  |  |  |  |  |  |  |
|  | - regular meetings with people |  |  |  |  |  |  |  |  |
|  | - meetings with population if any problem rises |  |  |  |  |  |  |  |  |
|  | - reception of people |  |  |  |  |  |  |  |  |
|  | - others (what exactly?) |  |  |  |  |  |  |  |  |
|  | Do you take part in such questioning, meetings, etc.? |  |  |  | #### Yes |  |  | No |  |
| 6 | What problems are the most important for you and the solution of which do you wait from the realization of sustainable development plan? (mark three most important problems) |  | Important |  | Wait for the solution from the realization of the strategy |  |  |  |  |
|  | - low salary |  |  |  |  |  |  |  |  |
|  | - lack of jobs |  |  |  |  |  |  |  |  |
|  | - housing problems |  |  |  |  |  |  |  |  |
|  | - communal sphere |  |  |  |  |  |  |  |  |
|  | - high prices |  |  |  |  |  |  |  |  |
|  | - medical service |  |  |  |  |  |  |  |  |
|  | - education |  |  |  |  |  |  |  |  |
|  | - culture |  |  |  |  |  |  |  |  |
|  | - ecology |  |  |  |  |  |  |  |  |
|  | - safety |  |  |  |  |  |  |  |  |
|  | - there are no places to spend leisure time |  |  |  |  |  |  |  |  |
|  | - different (what exactly?) |  |  |  |  |  |  |  |  |

| 7 |  |  | Whom did you apply for problem solution? |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | - head of Protochnoe village |  |  |  |  |  |  |  |  |
|  |  |  | - deputy of local government body |  |  |  |  |  |  |  |  |
|  |  |  | - raion deputy |  |  |  |  |  |  |  |  |
|  |  |  | - your deputy in State Duma |  |  |  |  |  |  |  |  |
|  |  |  | - other institutions (which of them exactly?) |  |  |  |  |  |  |  |  |
|  |  |  | Do you take part in questioning, meetings with deputies? |  |  |  |  | #### Yes |  |  | No |
|  |  |  | If yes, have they helped you to solve your problems? |  |  |  |  | #### Yes |  |  | No |
| 8 | Are there any committees (councils) of the territorial governing or interest clubs in your village? |  |  |  |  |  |  |  | #### Yes | No |  |
|  | Are you the member of these associations? |  |  |  |  |  |  |  | #### Yes | No |  |
|  | If “no”, why? |  |  |  |  |  |  |  |  |  |  |
|  | - nobody invites me |  |  |  |  |  |  |  |  |  |  |
|  | - I have no time |  |  |  |  |  |  |  |  |  |  |
|  | - they can’t help anyway |  |  |  |  |  |  |  |  |  |  |
|  | - other reasons (what exactly?) |  |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  | Are there enough small enterprises (trade, consumer services, productive and other cooperatives, etc.) in your village to satisfy all your needs? |  |  |  |  |  |  |  |
|  |  |  |  | - enough |  |  |  |  |  |  |  |
|  |  |  |  | - there are several, but they don’t cover all spheres |  |  |  |  |  |  |  |
|  |  |  |  | - only few |  |  |  |  |  |  |  |
|  |  |  |  | - it is difficult to say |  |  |  |  |  |  |  |
| 10 |  |  |  | How can you assess their activity? |  |  |  |  |  |  |  |
|  |  |  |  | - positively, they are necessary |  |  |  |  |  |  |  |
|  |  |  |  | - negatively (high prices, low quality, etc.) |  |  |  |  |  |  |  |
|  |  |  |  | - some of hem are good, some are bad, but still they are necessary |  |  |  |  |  |  |  |
|  |  |  |  | - it is difficult to say |  |  |  |  |  |  |  |
| 11 |  |  | Please, give information about yourself : |  |  |  |  |  |  |  |  |
|  |  |  | Sex |  | #### Male |  | Female |  |  |  |  |
|  |  |  | Age |  | 15-30 years | 31-60 years (for men) 31-55 (for women) | Over 60 years (for men) Over 55 (for women) |  |  |  |  |
|  |  |  | Your occupation? |  |  |  |  |  |  |  |  |
|  |  |  | Worker |  |  |  |  |  |  |  |  |
|  |  |  | Employee |  |  |  |  |  |  |  |  |
|  |  |  | State employee |  |  |  |  |  |  |  |  |
|  |  |  | Entrepreneur |  |  |  |  |  |  |  |  |
|  |  |  | Pupil |  |  |  |  |  |  |  |  |
|  |  |  | Housewife |  |  |  |  |  |  |  |  |
|  |  |  | Pensioner |  |  |  |  |  |  |  |  |
|  |  |  | Unemployed |  |  |  |  |  |  |  |  |
|  |  |  | Different (what exactly?) |  |  |  |  |  |  |  |  |
|  |  |  | Average income per m month per one person in your family |  |  |  |  |  |  |  |  |
|  |  |  | Less than 300 rubles |  |  |  |  |  |  |  |  |
|  |  |  | 300-500 rubles |  |  |  |  |  |  |  |  |
|  |  |  | 500-1000 rubles |  |  |  |  |  |  |  |  |
|  |  |  | 1000-1500 rubles |  |  |  |  |  |  |  |  |
|  |  |  | Over 1500 rubles |  |  |  |  |  |  |  |  |
| 12 |  | Fill in the enclosure to the questionnaire |  |  |  |  |  |  |  |  |  |

Thank you!

Questionnaire 2 for young people (from 15 to 30 years)

(Please fill in the questionnaire and hand in to the responsible executor)

Community Committee together with village administration is now working with the plan of sustainable development. This questionnaire was worked out to know people’s opinion about the problems in the village and the opportunities of sustainable development.

Please answer the questions giving a mark or a tick in the square of the answer. This questionnaire is anonymous but if you consider it necessary to tell something about yourself or give your comments, we would be very grateful.

| 1 | Do you know about elaboration of CSD plan in your community? | #### Yes | No |
| --- | --- | --- | --- |
|  | If “yes”, how did you know about it? |  |  |
|  | -presented at the meeting |  |  |
|  | -from the article in the raion newspaper (radio) |  |  |
|  | -differently (how exactly?) |  |  |

| 2 | Do you want to take part in writing the plan? | #### Yes | No |
| --- | --- | --- | --- |

| 3 | What do you think about CSD plan preparation? |  |
| --- | --- | --- |
|  | We hope that it will help us |  |
|  | These are only words, nothing will change |  |
|  | It is difficult to say |  |
|  | Differently (how exactly?) |  |

| 4 | How can you assess (from 1 to 5) young people’s opportunities in the village (1- do not exist or too bad, 2 – bad, 3 – satisfactory, 4 – good, 5 – excellent) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ## Opportunities |  |  |  |  |  |
|  | Jobs |  |  |  |  |  |
|  | Entertainment |  |  |  |  |  |
|  | Places for going in for sports |  |  |  |  |  |
|  | Arts / culture |  |  |  |  |  |
|  | Access to information including Internet |  |  |  |  |  |
|  | Café |  |  |  |  |  |
|  | Others |  |  |  |  |  |
|  | Comments to one or two questions |  |  |  |  |  |
| For example, to plant trees and gardens in the village, to create new jobs |  |  |  |  |  |  |
| 5 | How do you regard (from 1 to 5) the following existing problems of young people? This problem increases (+), stabilizes (0), decreases (-) | Scores | + |  | 0 | - |
|  | Violent crimes |  |  |  |  |  |
|  | Crimes without violence, stealing |  |  |  |  |  |
|  | Drugs |  |  |  |  |  |
|  | Alcoholism |  |  |  |  |  |
|  | Sexually transmitted diseases |  |  |  |  |  |
|  | Poverty |  |  |  |  |  |
|  | Different |  |  |  |  |  |

| 6 | ##### Do you want to stay in the village for living? | #### Yes | No |
| --- | --- | --- | --- |
|  | ##### If “no”, what can make you stay? | Mark an answer |  |
|  | ##### Favorable conditions for life |  |  |
|  | ##### Jobs |  |  |
|  | ##### Family reasons |  |  |
|  | ##### Clean village |  |  |
|  | ##### Different |  |  |

| 7 | ##### If you have an opportunity to realize one of the ideas to improve the quality of life for young people in the village, what would you do? | Answer (mark not more than 2 ideas) |
| --- | --- | --- |
|  | ##### Organize enterprises (say what enterprises are necessary) |  |
|  | ##### Create jobs |  |
|  | ##### Build sports grounds |  |
|  | ##### Plant trees and gardens, to light the village |  |
|  | ##### Replenish library with books |  |
|  | ##### Different |  |

| 8 |  | ##### Are there any clubs, sport associations, and interest clubs for the young in your village? | #### Yes | No |
| --- | --- | --- | --- | --- |
|  |  | ##### Are you the member o these clubs? | #### Yes | No |
|  | If “no”, why? |  |  |  |
|  | - nobody invites me |  |  |  |
|  | - I have no time |  |  |  |
|  | - they cannot help anyway |  |  |  |
|  | - different (what exactly?) |  |  |  |

| 9 |  | ##### Please, give some information about yourself: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Sex | #### Male |  |  | Female |  |
|  |  | Age | #### 15-17 |  | #### 18-20 | 21-25 | 26-30 |
|  | Occupation: |  |  |  |  |  |  |
|  | Worker |  |  |  |  |  |  |
|  | Employee |  |  |  |  |  |  |
|  | State employee |  |  |  |  |  |  |
|  | Entrepreneur |  |  |  |  |  |  |
|  | Pupil |  |  |  |  |  |  |
|  | Housewife |  |  |  |  |  |  |
|  | Unemployed |  |  |  |  |  |  |
|  | Different (what exactly?) |  |  |  |  |  |  |

|  | Your average income per month? |  |
| --- | --- | --- |
|  | Less than 300 rubles |  |
|  | 300-500 rubles |  |
|  | 500-1000 rubles |  |
|  | 1000-1500 rubles |  |
|  | over 1500 rubles |  |

| 10 | Fill in the enclosure to the questionnaire |
| --- | --- |

Thank you!

Enclosure to the questionnaire

(please fill in the questionnaire enclosure and return to a responsible executor )

The table contains a list of important village objects. Please mark 3 most important objects you would like to be included into sustainable development plan.

| № | Object |  |
| --- | --- | --- |
| 1 | School |  |
| 2 | Kindergarten |  |
| 3 | Culture house |  |
| 4 | Administration |  |
| 5 | Medical and obstetric station |  |
| 6 | Water pipeline |  |
| 7 | Post office |  |
| 8 | Sport ground |  |
| 9 | Technical water (irrigation) pipeline |  |
| 10 | Café |  |
| 11 | Shops |  |
| 12 | Bakery |  |
| 13 | Mini-market |  |
| 14 | Library |  |
| 15 | Office of the saving bank |  |
| 16 | Pump station |  |
| 17 | Bus station |  |
| 18 | Production (what exactly) |  |
| 19 | Different |  |

| 3 selected objects | Tasks to be solved |
| --- | --- |
| 3 selected objects | What resources and partners are needed to implement your ideas? |

Thank you!