## overall planning
Project title: |  |  |  |  | Project number: | [5 empty] | Country: | [5 empty] | Page: 1
Caspian Water Quality Monitoring and Action Plan for Areas of Pollution Concern |  |  |  |  | EuropeAid/122033/C/SV/Multi, TACIS/2005/ 109-244 | [5 empty] | AZ, KZ, RU, TM
Planning period: November 27th, 2006 - May 27th, 2009 |  |  |  |  | Prepared on: 09.07.07 | [5 empty] | EC Consultant: Consortium DHV BV (The Netherlands, leading party), COWI A/S (Denmark), ECORYS (The Netherlands) and WL¦Delft (The Netherlands)
Project objectives: To improve quality of the marine and coastal environment of the Caspian Sea through the Caspian Environment Program (CEP)
No | MAIN ACTIVITIES | TIME FRAME | [11 empty] | INPUTS
|  | 2006 | 2007 |  |  |  | 2008 |  |  |  | 2009 |  |  | PERSONNEL [working days] |  | EQUIPMENT AND MATERIAL |  | OTHER
|  | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | EC Consultant | Counterpart
Task 1 | Project Management | [12 empty] | 210+45 | 200 | Office rent, office operation, rent conference equipment |  | IAT, DSA, Visa out of duty station activities for staff and guests
Task 2 | Collection of existing data and identifying main pollution sources (FACILITARY TO 3, 4 and 5) | [12 empty] | AE
Task 3 | Design and implementation of an enhanced RWQMP | 2007 3: ru/az; 2007 4: tm/kz | 160 | 300
Task 4 | Deployment of equipment and procurement of vessels and samples analysis for four RWQMP surveys | 2007 3: Terek; 2007 4: Kos-at/Turkm.; 2008 1: Samur/Sam-Dag.; 2008 2: Kura/Cheleken; 2008 3: Absh /Ural /Volga; 2008 4: Turkm | 160 | 300 | Rent of boat- and boat trailer Procurement of proficiency testing
Task 5 | Production of RPAPs | 2007 3: Terek; 2008 1: Samur/Sam-Dag.; 2008 2: Kura/Cheleken; 2008 3: Absh /Ural /Volga | 110 | 200
other activities: | synchronize with Tacis Equipment supply tender, Tacis Black sea project
Regional workshops | bar: 2007 2; 2007 4; 2008 3; 2009 2
|  | 2008 4: TOTAL | 640+45 | 1000 | 320000 |  | EURO 150.000