## Sheet1
Project title: Caspian Water Quality Monitoring and Action Plan for Areas of Pollution Concern | Project number: EuropeAid/1220EuropeAid/122033/C/SV/Multi, TACIS/2005/ 109-244 | Country: AZ, KZ, RU, TM, |  | Page: 1
Planning period: November 27th, 2006 - May 27th, 2009 | Prepared on: 24.06.2007 | EC Consultant: Consortium DHV BV (The Netherlands, leading party), COWI A/S (Denmark), ECORYS (The Netherlands) and WL¦Delft (The Netherlands)
Outputs (to be described and target dates indicated | Agreed Objective Verifiable Indicators |  | Constrains and Assumptions
C/A
1. Developed enhanced Regional Water Quality Monitoring Programme (RWQMP) with progress on implementation | 1. Enhanced RWQMP approved by CEP and littoral states and first two years implemented |  | Continued commitment to CEP at national level
held 5 regional workshops |  |  | Scientic information shared freely between littoral states, according to First Convention of the Parties (COP1) of Tehran Convention, May 2007;
Statements of Endorsement, Visa and other documents are delivered in a timely and efficient manner
2. Successful planning, support and execution of four regional surveys as part of enhanced RWQMP | 2. Fulfillment of four regional surveys |  | Results complement CEP; no overlaps
First quarter of 2008, Survey KZ |  |  | Continued willingness by national governments to implement SAP
Second quarter of 2008, Survey RU |  |  | Equipment procured and delivered in time (AK)
Third quarter of 2008, Survey TM |  |  | Sufficient technical assistance to address relevant issues
Fourth quarter of 2008, Survey AZ |  |  | No dramatic additional environmental deterioration
Political support for water quality monitoring and regional pollution cleanup
3. A network of equipped and trained monitoring laboratories | 3. Deployment and utilization of equipment within lifetime of project |  | All Caspian countries will participate in the project
4. Development of agreed action plan and prioritized investment programme | 4. RPAP approved by CEP and littoral states within lifetime of project |  | The partner countries will allow procurement to take place on a tax free and hassle free basis
workshop Action planning